## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Shock and Awe |  |  |  |  | COMPANY NAME | [6 empty] | Particle Pistion Inc.
PROJECT MANAGER |  | Sir Lucas James Stanek the First |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Luke S | 2018-03-12 | 2018-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | Janez K | 2018-03-15 | 2018-03-16 | 1 | 100% | bar: WEEK 2 W
1.2 | Research | Tom D | 2018-03-15 | 2018-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Projections | Devin L | 2018-03-16 | 2018-03-22 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Stakeholders | Janez K | 2018-03-18 | 2018-03-22 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Guidelines | Tom D | 2018-03-19 | 2018-03-22 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation | Luke S | 2018-03-23 | 2018-03-23 | 0 | 50% | bar: WEEK 3 F
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Luke S | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | Budget | Janez K | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Communication Plan | Tom D |  |  | 0 | 0% | bar: WEEK 5 W to WEEK 6 R
2.4 | Risk Management | Devin L |  |  | 0 | 0% | bar: WEEK 5 F to WEEK 6 F
3 | Project Conception and Initiation
3.1 | Status and Tracking | Luke S |  |  | 0 | 0%
3.2 | KPIs | Janez K |  |  | 0 | 0%
3.2.1 | Monitoring | Tom D |  |  | 0 | 0%
3.2.2 | Forecasts | Devin L |  |  | 0 | 0%
3.3 | Project Updates | Tom D |  |  | 0 | 0%
3.3.1 | Chart Updates | Luke S |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Luke S |  |  | 0 | 0%
4.2 | Quality Deliverables | Devin L |  |  | 0 | 0%
4.3 | Effort and Cost Tracking | Tom D |  |  | 0 | 0%
4.4 | Project Performance | Luke S |  |  | 0 | 0%